## Index_Page
DONBOSCO HOSPITAL
Version No: |  |  |  | Tested By: Geethu K M
Verified By: |  |  |  | Date: 23/07/2023
Test Id | Test Description | Test Procedure | Test Data | Expected Result | Actual Result | Status
DON_HM_01 | Verify that the Donbosco logo is correctly displayed on the Home page | 1. Open Donboscco website 2.Look for the logo image on the home page. 3. Verify that the logo is displayed in the correct location on the page. 4. Verify that the logo is of the correct size,color and font. 5. Verify that the logo image is clear and not distorted. | https://www.donboscohospital.com/index.html | The logo image should be correctly displayed on the home page | The logo image is correctly displayed on the home page | Pass
DON_HM_02 | Verify that the user is redirected to home page when user click on the logo | 1. Open Donboscco website. 2. Look for the logo on the home page. 3. Verify that the user is redirected home page. | https://www.donboscohospital.com/index.html | The user should be redirected to home page | The user is redirected to home page | Pass
DON_HM_03 | Verify that the Hamburger Menu is working properly | 1. Open Donboscco website. 2. Look for the Hamburger Menu. 3. Click on the Hamburger Menu. 4. Verify that all the links under hamburger Menu is displayed. 5. Again click on the hamburger Menu and verify that the links are hidden from the home page. | https://www.donboscohospital.com/index.html | The Hamburger Menu should be working properly | The Hamburger Menu is working properly | Pass
DON_HM_04 | Verify that all the menus are present as per the requirement by clicking on the Hamburger Menu in home page. | 1. Open Donboscco website. 2. Look for the Hamburger Menu. 3. Click on the HamburgerMenu. 4. Verify that Home, About, Departments, Doctors, Charity, Academics, Health Checkups, Career and Contact menus are present. | https://www.donboscohospital.com/index.html | The Home, About, Departments, Doctors, Charity, Academics, Health Checkups, Career and Contact menus should be present in home page. | The Home, About, Departments, Doctors, Charity, Academics, Health Checkups, Career and Contact menus are present in home page. | Pass
DON_HM_05 | Verify that all the menus under hamburger Menu is redirected to respective pages | 1. Open Donbosco website. 2. Click on the Hamburger Menu. 3. Click on each of the menu. 4. Verify that the user is redirected to respective pages. |  | All the menus should be redirected to respective pages. | All the menus are redirected to respective pages. | Pass
DON_HM_06 | Verify all the department buttons in Index Page | 1. Open Donbosco website. 2. Click on every Department Button 3. Verify the department description is changed by clicking on the each department. |  | Department description should be changed. | Department description is changed | Pass
DON_HM_07 | Verify learn more button in Department description. | 1. Open Donbosco website. 2. Click on every Department Button 3. Verify the learn more button in department decription. |  | Learn more button should be working properly | Learn more button is not working properly. | Fail
DON_HM_08 | Verify the services in index page | 1. Open Donbosco website. 2. Click on every Services link. 3. Verify that the each service is redirecting to respective pages. |  | Service links should be redirecting to respective pages. | Service links are not redirecting to respective pages. | Fail
DON_HM_09 | Verify all the experienced doctors are listed in index page | 1. Open Donbosco website. 2. Verify all the experienced doctors are listed in index page. |  | All experienced doctors should be listed in index page. | All experienced doctors are listed in index page. | Pass
DON_HM_10 | Verify the Gallery in index page | 1. Open Donbosco website 2. verify the images of gallery are correct size and order |  | Images of gallery should be correct size and order as per the requirement | Some of the images are not in the same size | Fail
DON_HM_11 | Verify the Testimonials in index page. | 1. Open Donbosco website 2. verify each testimonial has owners name. |  | Each testimonials should have owners name | Each testimonial having owners name | Pass
DON_HM_12 | Verify the Testimonials in index page. | 1. Open Donbosco website 2. Click on more button in testimonials. 3. Verify each more button is properly working. |  | More button should be working properly. | More button is working properly | Pass
DON_HM_13 | Verify the Testimonials in index page. | 1. Open Donbosco website 2. Click on Google review link in testimonials. 3. Verify each Google review link. |  | Google review link should be redirecting to corresponding pages | The link is not working | Fail
DON_HM_14 | Verify the left and right arrows in testimonials | 1. Open Donboscco website. 2. Look for the testimonials. 3. Click on left arrow. 4. Verify the content displayed. 5. Click on right arrow. 6. Verify the content displayed. |  | The content should be loaded from forword and backword by clicking on the left and right arrow respectively. | The content is loaded from forword and backword by clicking on the left and right arrow respectively. | Pass
DON_HM_15 | Verify all the social media linksin footer section properly working | 1. Open Donboscco website. 2. Click all the links 3. Verify the links are working |  | The Social medias links should be redirecting to respective pages. | The links are not redirecting to respective pages | Fail
DON_HM_16 | Verify all the other links in footer section. | 1. Open Donboscco website. 2. Click on each link. 3. Verify all the links are redirecting respective pages. |  | The other links in footer section should be redirecting to respective pages. | The charity, accademics, email, phone call links are not redirecting to respective pages. | Fail
DON_HM_17 | Verify the floating buttons. | 1. Open Donboscco website. 2. Click on each floating button. 3. Verify all the icons are redirecting respective pages. |  | The floating buttons should be working properly | The medication button is not working. | Fail
DON_HM_18 | Verify the another "Book Appointment Button" in Index Page | 1. Open Donbosco website. 2. Click on the Book Appointment Button. 3. Verify that the Book Appointment Button should be redirected to booking section of website |  | It should be redirected to booking section. | It is redirecting to booking section. | Pass
DON_HM_19 | Verify the Book Appointment Button in home page | 1. Open Donboscco website. 2. Click on Book Appointment button. 3. Verify all the fields are displayed as per the requirement. |  | All the fields should be displayed. | All the fields are displayed. | Pass
DON_HM_20 | Verify the Book Appointment Button in home page | 1. Open Donboscco website. 2. Click on Book Appointment button. 3. Click on send message button in Book appointment form without entering the data. 4. Verify user is able to booking. |  | The user should be prompt an error message. | The user is not prompt an error message. | Fail
DON_HM_21 | Verify the Book Appointment Button in home page | 1. Open Donboscco website. 2. Click on Book Appointment button. 3. Click on send message button by entering wrong details. 4. Verify user is able to booking. | abcdefghijklmnopqrs a@gmail.com 5/24/2023 12:00 am aaa | The user should be prompt an error message. | No error message is prompted. | Fail
DON_HM_22 | Verify the Book Appointment Button in home page | 1. Open Donboscco website. 2. Click on Book Appointment button. 3. Click on send message button by entering valid details. 4. Verify user is able to booking. | Geethu K M geethukm23@gmail.com 09/27/2023 10:00am Endocrynology | The user should be able booking | The user is not able to booking. | Fail

## About&Department
DONBOSCO HOSPITAL
OS: Windows 11 |  |  |  | Tested By: Geethu K M
Verified By: |  |  |  | Date:15/08/2023
Test Id | Test Description | Test Procedure | Test Data | Expected Result | Actual Result | Status
DON_AB_DP_01 | Verify the title ABOUT US is correctly displayed on the page. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on About link. 4. Verify the title is displayed as per the requirement. |  | Title should be displayed at the center. | Title is not displayed at the center. | Fail
DON_AB_DP_02 | Verify the facilities. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on About link. 4. Verify all the facilities are displayed in the facilities section. |  | All the facilities should be displayed in the facilities section. | All the facilities are displayed in the facilities section. | Pass
DON_AB_DP_03 | Verify Administrators. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on About link. 4. Verify all the administrators displayed in the adminstrators section. |  | All the administrators should be displayed in the administrators section. | All the administrators are displayed. | Pass
DON_AB_DP_04 | Verify Administrators. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on About link. 4. Verify the administrators slide is turned when a mouse is point to the slide. |  | Administrators slide should be turned when a mouse is point to the slide. | Administrators slide is turned. | Pass
DON_AB_DP_05 | Verify Administrators. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on About link. 4. Verify the administrators feedback is displayed in the opposite side of the slide. |  | Administrators feedback should be displayed in the opposite side of the slide. | Not all the slide display's administrators feedback. | Fail
DON_AB_DP_06 | Verify the title Departments is correctly displayed on the page. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Department link. 4. Verify the title is displayed as per the requirement. |  | Title should be displayed at the center. | Title is not displayed at the center. | Fail
DON_AB_DP_07 | Verify Departments. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Department link. 4. Verify all the departments are displayed. |  | All the departments should be displayed in the departments section. | All the departments are displayed in the departments section. | Pass
DON_AB_DP_08 | Verify Departments. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Department link. 4. Click on + button. 5. Verify it is expanded. 6. Click on - button. 7. Verify it is truncated. |  | It should be expand and truncate contents by clicking on th + and - buttons | It is expanded and truncated. | Pass
DON_AB_DP_09 | Verify Departments. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Department link. 4. Click on + button. 5. Click on know more button in each department link. 6. Verify it is redirected to respective page. |  | It should be redirected to respective pages. | The link is not clickable | Fail

## Doctors
DONBOSCO HOSPITAL
OS: Windows 11 |  |  |  | Tested By: Geethu K M
Verified By: |  |  |  | Date:23/08/2023
Test Id | Test Description | Test Procedure | Test Data | Expected Result | Actual Result | Status
DON_DR_01 | Verify the title WELL EXPERIENCED DOCTORS is correctly displayed on the page. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Doctors link. 4. Verify the title is displayed as per the requirement. |  | Title should be displayed at the center. | Title is not displayed at the center. | Fail
DON_DR_02 | Verify the subtitle. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Doctors link. 4. Verify the subtitle is displayed as per the requirement. |  | Each words of subtittle should be started with capital letters. | Not all the words started with capital letter. | Fail
DON_DR_03 | Verify all the doctors are displayed in the page. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Doctors link. 4. Verify all the doctors are displayed on the page. |  | All the doctors should be displayed on the page. | Doctors are displayed on the page. | Pass
DON_DR_04 | Verify doctotors are displayed using filter. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Doctors link. 4. Click on each department in the filter. 5. Verify doctors are displayed corresponding to their department. |  | Doctors should be displayed corresponding to their department | First 4 department shows the respective doctors and remainig departments doesnot shows doctors. | Fail
DON_DR_05 | Verify Doctors flipper | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Doctors link. 4. Verify All the doctors have an image with their details. |  | The listed doctors should have an image with their department details. | Some of the listed doctors doesnt have images. | Fail
DON_DR_06 | Verify Doctors flipper | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Doctors link. 4. Verify the opposite side of the flipper have the doctors qualification and OP timings. |  | It should have the doctors medical qualification and OP timings. | Some of the doctors doesnt have op timing. | Fail
DON_DR_07 | Verify Doctors flipper | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Doctors link. 4. Turn over the flipper. 5. Click on BookAppointment button. 6. Verify the button is working. |  | BookAppointment button should be redirecting to respective page. | The button is not clickable. | Fail

## Charity&Accademics
DONBOSCO HOSPITAL
OS: Windows 11 |  |  |  | Tested By: Geethu K M
Verified By: |  |  |  | Date: 01/09/2023
Test Id | Test Description | Test Procedure | Test Data | Expected Result | Actual Result | Status
DB_CH_AC_01 | Verify the title CHARITY is correctly displayed on the page. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Charity link. 4. Verify the title is displayed as per the requirement. |  | Title should be displayed at the center. | Title is not displayed at the center. | Fail
DB_CH_AC_02 | Verify all the charities are displayed with images properly. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Charity link. 4. Verify the title is displayed as per the requirement. |  | All the charity work should be displayed properly. | All the charity works are displayed correctly. | Pass.
DB_CH_AC_03 | Verify the title ACCADEMICS is correctly displayed on the page. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Accademics link. 4. Verify the title is displayed as per the requirement. |  | Title should be displayed at the center. | Title is not displayed at the center. | Fail
DB_CH_AC_04 | Verify all the accademics offered displayed correctly. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Accademics link. |  | All the accademics offered should be displayed properly | All the accademics are properly displayed. | Pass.
DB_CH_AC_05 | Verify the accademics offered. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Accademics link. 4. Verify the icon for expanding the course details. |  | The expand icon should be + cirlce. | The expand icon is - circle. | Fail
DB_CH_AC_06 | Verify the accademics offered. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Accademics link. 4. Click on - icon. 5. Verify the course details are displayed as per the requirement. |  | The course details should be displayed as per the requirement. | The course details are displayed as per the requirement. | Pass.
DB_CH_AC_07 | Verify the accademics offered. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Accademics link. 4. Click on - icon. 5. Verify the Download Application button. |  | The Download Application button should be download the application. | The button is not clickable. | Fail.

## Healthcheckup,Career&Contact
DONBOSCO HOSPITAL
OS: Windows 11 |  |  |  | Tested By: Geethu K M
Verified By: |  |  |  | Date:02/09/2023
Test Id | Test Description | Test Procedure | Test Data | Expected Result | Actual Result | Status
DB_H_CR_CO_01 | Verify the title HEALTH CHECK UPS is correctly displayed on the page. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Health Checkups link. 4. Verify the title is displayed as per the requirement. |  | Title should be displayed at the center. | Title is not displayed at the center. | Fail
DB_H_CR_CO_02 | Verify Health Packages and instructions are as per the requirement. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Health Checkups link. 4. Verify Health packages and instructions are as per the requirement. |  | Health packages and instructions should be as per the requirement. | Health packages and instructions are as per the requirements. | Pass
DB_H_CR_CO_03 | Verify the mob no in instructions | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Health Checkups link. 4. Verify the mob no in instructions. |  | It should be redirecting to direct calling service. | It is not redirecting to direct calling. | Fail
DB_H_CR_CO_04 | Verify all the Health Checkups are as per the requirement. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Health Checkups link. 4. Click on each Health Checkups. 5. Verify each Health Checkup is as per the requirement. |  | Health Checkups should be as per the requirement. | Health Packages are as per the requirement. | Pass
DB_H_CR_CO_05 | Verify the title CAREER is correctly displayed on the page. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Career link. 4. Verify the title is displayed as per the requirement. |  | Title should be displayed at the center. | Title is not displayed at the center. | Fail
DB_H_CR_CO_06 | Verify all the vaccancies are displayed in career oppertunity section. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Career link. 4. Verify all the vaccancies are displayed. |  | All the vaccancies should be displayed in the career oppertunity section. | All the vaccancies are displayed. | Pass
DB_H_CR_CO_07 | Verify Apply Now button. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Career link. 4. Verify Apply Now button. |  | Apply Now button should be able to allow the user for applying the job. | The button is not working. | Fail
DB_H_CR_CO_08 | Verify the Contact page. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Contact link. |  | Contact page should be display contact details. | The page is displaying book appointment section. | Fail

## BugReport
DONBOSCO HOSPITAL
OS: Windows 11 |  |  |  | Date: 10/09/2023
Verified By: |  |  |  | Tested By: Geethu K M
Bug Id | TestId | Expected Result | Bug Description | Steps to Reproduce | Screenshot | Severity | Priority | Status
DEF_DON_01 | DON_HM_07 | Learn more button should be working properly | Learn more button is not working properly. | 1. Open Donbosco website. 2. Click on every Department Button 3. Verify the learn more button in department decription. |  | Major | P11 | New
DEF_DON_02 | DON_HM_08 | Service links should be redirecting to respective pages. | Service links are not redirecting to respective pages. | 1. Open Donbosco website. 2. Click on every Services link. 3. Verify that the each service is redirecting to respective pages. |  | Major | P12 | New
DEF_DON_03 | DON_HM_10 | Images of gallery should be correct size and order as per the requirement | Some of the images are not in the same size | 1. Open Donbosco website 2. verify the images of gallery are correct size and order |  | Minor | P21 | New
DEF_DON_04 | DON_HM_13 | Google review link should be redirecting to corresponding pages | The link is not working | 1. Open Donbosco website 2. Click on Google review link in testimonials. 3. Verify each Google review link. |  | Major | P13 | New
DEF_DON_05 | DON_HM_15 | The Social Medias links should be redirecting to respective pages. | The links are not redirecting to respective pages | 1. Open Donboscco website. 2. Click all the links 3. Verify the links are working |  | Major | P14 | New
DEF_DON_06 | DON_HM_16 | The other links in footer section should be redirecting to respective pages. | The charity, accademics, email, phone call links are not redirecting to respective pages. | 1. Open Donboscco website. 2. Click on each link. 3. Verify all the links are redirecting respective pages. |  | Major | P15 | New
DEF_DON_07 | DON_HM_17 | The floating buttons should be working properly | The medication button is not working. | 1. Open Donboscco website. 2. Click on each floating button. 3. Verify all the icons are redirecting respective pages. |  | Major | P9 | New
DEF_DON_08 | DON_HM_20 | The user should be prompt an error message. | The user is not prompt an error message. | 1. Open Donboscco website. 2. Click on Book Appointment button. 3. Click on send message button in Book appointment form without entering the data. 4. Verify user is able to booking. |  | Major | P16 | New
DEF_DON_09 | DON_HM_21 | The user should be prompt an error message. | No error message is prompted. | 1. Open Donboscco website. 2. Click on Book Appointment button. 3. Click on send message button by entering wrong details. 4. Verify user is able to booking. |  | Major | P17 | New
DEF_DON_10 | DON_HM_22 | The user should be able to booking | The user is not able to booking. | 1. Open Donboscco website. 2. Click on Book Appointment button. 3. Click on send message button by entering valid details. 4. Verify user is able to booking. |  | Critical | P1 | New
DEF_DON_11 | DON_AB_DP_01 | Title should be displayed at the center. | Title is not displayed at the center. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on About link. 4. Verify the title is displayed as per the requirement. |  | Minor | P22 | New
DEF_DON_12 | DON_AB_DP_05 | Administrators feedback should be displayed in the opposite side of the slide. | Not all the slide display's administrators feedback. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on About link. 4. Verify the administrators feedback is displayed in the opposite side of the slide. |  | Major | P20 | New
DEF_DON_13 | DON_AB_DP_06 | Title should be displayed at the center. | Title is not displayed at the center. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Department link. 4. Verify the title is displayed as per the requirement. |  | Minor | P23 | New
DEF_DON_14 | DON_AB_DP_09 | The know more button should be redirected to respective pages. | The link is not clickable | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Department link. 4. Click on + button. 5. Click on know more button in each department link. 6. Verify it is redirected to respective page. |  | Major | P10 | New
DEF_DON_15 | DON_DR_01 | Title should be displayed at the center. | Title is not displayed at the center. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Doctors link. 4. Verify the title is displayed as per the requirement. |  | Minor | P24 | New
DEF_DON_16 | DON_DR_02 | Each words of subtittle should be started with capital letters. | Not all the words started with capital letter. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Doctors link. 4. Verify the subtitle is displayed as per the requirement. |  | Trivial | P29 | New
DEF_DON_17 | DON_DR_04 | Doctors should be displayed corresponding to their department | First 4 department shows the respective doctors and remainig departments doesnot shows doctors. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Doctors link. 4. Click on each department in the filter. 5. Verify doctors are displayed corresponding to their department. |  | Major | P6 | New
DEF_DON_18 | DON_DR_05 | The listed doctors should have an image with their department details. | Some of the listed doctors doesnt have images. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Doctors link. 4. Verify All the doctors have an image with their details. |  | Major | P7 | New
DEF_DON_19 | DON_DR_06 | It should have the doctors medical qualification and OP timings. | Some of the doctors doesnt have op timing. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Doctors link. 4. Verify the opposite side of the flipper have the doctors qualification and OP timings. |  | Major | P8 | New
DEF_DON_20 | DON_DR_07 | Book Appointment button should be redirecting to respective page. | The button is not clickable. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Doctors link. 4. Turn over the flipper. 5. Click on BookAppointment button. 6. Verify the button is working. |  | Critical | P2 | New
DEF_DON_21 | DB_CH_AC_01 | Title should be displayed at the center. | Title is not displayed at the center. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Charity link. 4. Verify the title is displayed as per the requirement. |  | Minor | P25 | New
DEF_DON_22 | DB_CH_AC_03 | Title should be displayed at the center. | Title is not displayed at the center. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Accademics link. 4. Verify the title is displayed as per the requirement. |  | Minor | P26 | New
DEF_DON_23 | DB_CH_AC_05 | The expand icon should be + cirlce. | The expand icon is - circle. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Accademics link. 4. Verify the icon for expanding the course details. |  | Major | P19 | New
DEF_DON_24 | DB_CH_AC_07 | The Download Application button should be download the application. | The button is not clickable. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Accademics link. 4. Click on - icon. 5. Verify the Download Application button. |  | Critical | P3 | New
DEF_DON_25 | DB_H_CR_CO_01 | Title should be displayed at the center. | Title is not displayed at the center. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Health Checkups link. 4. Verify the title is displayed as per the requirement. |  | Minor | P27 | New
DEF_DON_26 | DB_H_CR_CO_03 | Mob no should be redirecting to direct calling service. | It is not redirecting to direct calling. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Health Checkups link. 4. Verify the mob no in instructions. |  | Major | P18 | New
DEF_DON_27 | DB_H_CR_CO_05 | Title should be displayed at the center. | Title is not displayed at the center. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Career link. 4. Verify the title is displayed as per the requirement. |  | Minor | P28 | New
DEF_DON_28 | DB_H_CR_CO_07 | Apply Now button should be able to allow the user for applying the job. | The button is not working. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Career link. 4. Verify Apply Now button. |  | Critical | P4 | New
DEF_DON_29 | DB_H_CR_CO_08 | Contact page should be display contact details. | The page is displaying book appointment section. | 1.Open Donboscco Website. 2. Click on hamburger button. 3. Click on Contact link. |  | Major | P5 | New

## Test Report
Sl No | Module Name | Testcase Passed | Testcase Failed | Total Testcases
1 | Index Page | 12 | 10 | 22
2 | About&Department | 5 | 4 | 9
3 | Doctors | 1 | 6 | 7
4 | Charity&Accademics | 3 | 4 | 7
5 | HealthCheckups,Career&Contact | 3 | 5 | 8

## Distribution Graph
DEFECT DISTRIBUTION GRAPH
MODULE NAME | DEFECT DISTRIBUTION
Index Page | 10
About&Department | 4
Doctors | 6
Charity&Accademics | 4
Healthcheckups,Career & Contact | 5